## 0 Summary
GARUDA Core — Verification Plan
Block I, the RV32IM pipeline. Phases mirror '1Tops RISC-V SoC Verification Strategy v1'. The DSU has its own plan: tb/dsu/GARUDA_DSU_Verification_Plan.xlsx
# | Test | What could go wrong / what it checks | How I test it | Expected result | Pri | Done
Phase 1 — Unit (per-module inside the core)
1 | Scope | 26 modules in rtl/core + 14 in rtl/dsu | Directed + constrained-random per module, task-based SV TB | All P0 rows pass; functional coverage goals met per block | P0 | In progress
2 | Status today | 6 of 26 core modules have any TB at all | ex_smoke, id_ex_fwd, exmem_ifid, pipe_ctrl, csr_file, trap_ctrl | 20 modules unverified; 0 modules have covergroups | P0
Phase 2 — Core Sanity TB
3 | Scope | garuda_core_top + I/D memory models + IRQ stimulus | Hand-written instruction sequences via $readmemh | Every instruction class executes; hazards and traps behave | P0 | Not started
4 | Blocker | needs AHB-Lite memory models (not AXI) | Cadence AHB VIP, or hand-written behavioural slave | Wait states + ERROR responses injectable | P0
Phase 3 — Core ISA / ISS lockstep
5 | Scope | riscv-arch-test + riscv-dv streams vs Spike | Compile with riscv-gnu-toolchain, run both, diff logs | Signature match on all rv32ui/rv32um; 1k+ dv seeds clean | P0 | Not started
6 | Blocker | Spike does not know Custom-0 or CLIC | Extend Spike via custom-extension hook -> DSU golden model | DSU instrs retire in Spike with correct GPR/acc effects | P0 | Needs decision
Phase 4 — SoC without core
7 | Scope | interconnect + peripheral subsystem, UVM agent | UVM AHB master agent driving the bus in place of the core | Register coverage 100%; interrupt paths end-to-end | P1 | BLOCKED
8 | Blocker | rtl/ahb, rtl/apb, rtl/uart, rtl/gpio, rtl/i2c, rtl/spi_*, rtl/timers, rtl/plic, rtl/clic, rtl/dma are ALL empty directories | n/a — no RTL exists to verify | Cannot start until SoC RTL is written | P1 | BLOCKED
Phase 5 — Full SoC with core
9 | Scope | boot + bare-metal regressions + long runs | C tests via riscv-gnu-toolchain, boot from BROM | Boot success; full regression clean; no deadlocks | P1 | BLOCKED
10 | Blocker | depends on Phase 4 and on the SoC RTL existing | n/a | Cannot start | P1 | BLOCKED
Cross-cutting
11 | DSU verification | Block II — the reason the chip exists | Golden model + generated vectors + directed TB (see DSU sheet) | All P0 DSU rows pass against DSUModel cycle-accurate compare | P0 | In progress
12 | Formal (JasperGold) | control blocks whose state space simulation only samples | FPV on pipe_ctrl, trap_ctrl, forward_unit, hazard_forward_unit | Priority/mutex properties proven, not just simulated | P1 | Not started
13 | Coverage closure | signoff is coverage, not 'it ran once' | Xcelium covergroups + vManager merge across all regressions | Functional goals met; code coverage 95% with waivers | P0 | Not started

## 1 Unit
Phase 1 — Unit Level (module inside the core)
Strategy doc §2. One section per module in rtl/core. 'Done' = PASS means a testbench exists and passes today.
# | Test | What could go wrong / what it checks | How I test it | Expected result | Pri | Done
IF stage — garuda_pc_gen.v
1 | reset vector | PC must come out of reset at RESET_VECTOR or the core fetches garbage from cycle 0 | release reset, sample first I-port address | haddr == RESET_VECTOR (parameterised, default 0x1000_0000) | P0
2 | sequential increment | PC must advance by 4 only when IF actually accepts — double-increment loses an instruction silently | hold stall_i high/low across accepts | PC+4 exactly once per accept | P0
3 | redirect priority | trap must beat EX redirect must beat ID redirect; wrong order fetches from the wrong target after a trap | assert all three redirect sources in the same cycle | trap target wins, then EX, then ID | P0
4 | no advance under backpressure | PC advancing while downstream is stalled drops instructions | stall_i high for N cycles with valid fetch | PC frozen for all N | P0
IF stage — garuda_iport_ahb_master.v
5 | AHB address/data phase | protocol violation hangs the bus | drive HREADY low for 1..N cycles mid-transfer | HTRANS/HADDR held stable through the wait; no new transfer started | P0
6 | drop_pending hazard | redirect arriving while a fetch is outstanding must discard the returning data, not inject it after the flush | assert redirect_i with fetch_outstanding high | data_valid_o stays low for the discarded beat | P0
7 | HRESP ERROR | a bus error must become an instruction access fault (cause 1), not a silent wrong instruction | slave returns ERROR two-cycle response | instr_fault_o asserted with the right PC | P0
IF stage — garuda_prefetch_buffer.v
8 | fill/drain | buffer must never return a stale instruction after a redirect | fill buffer, redirect, check next delivered instruction | buffer flushed; next instr is from the redirect target | P0
9 | full/empty corners | overflow or underflow corrupts instruction order | back-to-back accepts with stalled consumer | no instruction lost or duplicated | P0
ID stage — decode_control.v
10 | all RV32I opcodes | a wrong control bit is a silent wrong answer, and the wild-goose-chase class of bug | sweep every legal opcode x funct3 x funct7 combination | control bundle matches a reference table | P0
11 | M-extension detect | funct7 = 0000001 must select MUL/DIV/REM | sweep all 8 M-ops | mul_en asserted, correct funct3 forwarded | P0
12 | writeback select | ALU vs LOAD vs PC+4 confusion writes the wrong value to the register file | one instruction of each class | mem_to_reg / reg_write correct | P0
13 | illegal detection | an undecodable word must raise illegal, not execute as something else | sweep unused opcodes and reserved funct combinations | illegal_instr_dec asserted, all enables low | P0
14 | Custom-0 passthrough | DSU opcode must set dsu_en and not be treated as illegal by the base decoder | all 10 Custom-0 funct5 values | dsu_en high, illegal low | P0
ID stage — imm_gen.v
15 | I/S/B/U/J formats | wrong immediate = wrong branch target or wrong address; classic silent failure | directed vectors per format incl. all-ones and sign boundaries | matches a reference immediate extractor | P0
16 | sign extension | unsigned-extending a negative immediate breaks backwards branches | negative immediates in every format | correctly sign-extended to 32b | P0
ID stage — regfile.v
17 | x0 hardwired | a write to x0 that sticks corrupts everything downstream | write non-zero to x0, read back | reads 0 | P0
18 | same-cycle write/read | the WB->ID bypass policy must be defined and implemented consistently (write-first vs read-first) | write and read the same register in one cycle | documented policy holds — write-first per Sec.7 | P0
19 | dual read ports | rs1/rs2 crosstalk | read two different registers simultaneously, including the same register on both ports | both ports return the correct value | P1
ID stage — branch_predict.v
20 | static direction | backward-taken / forward-not-taken policy must match what EX compares against, or every branch mispredicts | backward and forward branch offsets | predict_taken matches the documented static policy | P0
21 | target computation | wrong predicted target wastes the redirect | sweep branch offsets | target = PC + imm | P0
ID stage — hazard_forward_unit.v / load_use
22 | load-use detect | missing a load-use stall reads stale register data | LOAD followed immediately by a dependent op on rs1, rs2, and both | load_use_stall asserted for exactly one cycle | P0
23 | no false stall | over-stalling on x0 or on a non-load kills performance and can mask real bugs | LOAD with rd=x0 then dependent op; ALU op then dependent op | no stall | P1
EX — alu.v
24 | ADD/SUB wrap | overflow must wrap two's complement, not saturate | 0x7FFFFFFF+1, 0x80000000-1 | wraps, no trap | P0
25 | shift amount masking | RV32 masks the shift amount to 5 bits; not masking gives 0 where the ISA says otherwise | shift amounts 0, 1, 31, 32, 63 | amount masked to [4:0] | P0
26 | SRL vs SRA | logical vs arithmetic confusion breaks signed division idioms | negative operand, both shift ops | SRA keeps sign, SRL zero-fills | P0
27 | SLT/SLTU sign | signed/unsigned compare confusion around the sign bit | pairs straddling 0x80000000 | matches signed and unsigned semantics respectively | P0
EX — mul32.v
28 | MUL/MULH/MULHSU/MULHU | the three high-half variants differ only in signedness and are very easy to get wrong | corner operand matrix incl. 0x80000000 x 0x80000000 | matches a Python reference for all four | P0
29 | DIV/REM by zero | the ISA mandates specific results, not a trap | divide and remainder by zero | DIV=-1 (all ones), REM=dividend, per RISC-V spec | P0
30 | DIV overflow | -2^31 / -1 is the one overflow case in the ISA | 0x80000000 / 0xFFFFFFFF | DIV=0x80000000, REM=0 | P0
31 | latency / backpressure | multi-cycle units are where handshake bugs hide | issue back-to-back multiplies with EX stalled | deterministic or bounded latency; no lost result | P0
EX — branch_unit.v
32 | compare matrix | a wrong compare sends control flow to the wrong place and looks like a random crash | BEQ/BNE/BLT/BGE/BLTU/BGEU with rs1<rs2, ==, > | full 6x3 matrix matches reference | P0
33 | sign-bit boundary | signed vs unsigned compare divergence | operands straddling 0x80000000 | signed and unsigned differ correctly | P0
EX — csr_rw.v
34 | RW/RS/RC semantics | read-modify-write must read the OLD value and write the new one in the same instruction | CSRRW/S/C with known prior CSR value | rd gets old value, CSR gets new | P0
35 | rs1=x0 / uimm=0 | RS/RC with a zero operand must NOT write (else you corrupt read-only-ish CSRs by reading them) | CSRRS/CSRRC with rs1=x0 | no write occurs | P0
36 | immediate variants | CSRRWI/SI/CI take a 5-bit uimm, not a register | all three immediate forms | uimm zero-extended, not sign-extended | P0
EX — forward_unit.v
37 | EX/MEM over MEM/WB | when both stages can forward the same register, the YOUNGER value must win or you read stale data | same rd in EX/MEM and MEM/WB, dependent op in EX | EX/MEM forwarded | P0
38 | x0 never forwarded | forwarding a write to x0 injects garbage | instruction with rd=x0 followed by a dependent read | no forward; regfile 0 used | P0
39 | reg_write gating | forwarding from an instruction that isn't writing is a pure data-corruption bug | store/branch (reg_write=0) followed by dependent op | no forward | P0
40 | FORMAL | the select priority is a small combinational lattice — prove it rather than sample it | JasperGold FPV: assert one-hot select and correct priority | properties proven | P1
EX — ex_stage.v (result mux + DSU boundary)
41 | result mux priority | Sec.9.2 erratum: csr_rdata > dsu > mul > alu. A wrong order breaks CSRRW read-modify-write | issue CSR, DSU, MUL and ALU ops incl. overlapping enables | documented priority holds | P0
42 | dsu_rd_valid gating | ex_mem must capture the DSU result on dsu_rd_valid, NOT on dsu_en (valid self-gates during a busy hold) | DSU op that stalls (dsu_busy) then completes | no capture while busy; capture exactly once on valid | P0
43 | rd_out source | the DSU owns rd when it writes back; taking rd from the base decoder instead writes the wrong register | DSU readback op with rd != base-decoded rd | rd_out = dsu_rd_addr when dsu_rd_valid | P0
MEM — load_store_unit.v
44 | byte enables | wrong BE for address[1:0] corrupts neighbouring bytes — a classic silicon escape | SB/SH/SW at every offset 0..3 | HSIZE and write-data lane correct | P0
45 | store data alignment | store data must be replicated into the right lane for sub-word stores | SB/SH at all offsets | hwdata lane matches address | P0
46 | misalignment detect | a misaligned access must be killed BEFORE the bus address phase commits | LW at offset 1/2/3, LH at odd offset | misaligned flagged, no bus transfer started | P0
MEM — load_formatter.v
47 | sign vs zero extend | LB/LH vs LBU/LHU confusion is silent and common | negative byte/half at every offset | LB/LH sign-extend, LBU/LHU zero-extend | P0
48 | offset extraction | the wrong byte lane returns a plausible-but-wrong value | all size x offset combinations | correct lane selected for each | P0
MEM — d_port_ahb_master.v
49 | wait states | the pipeline must freeze, not drop, during HREADY low | random 0..N wait states on every access | mem_stall asserted; transfer completes intact | P0
50 | HRESP ERROR | must become load/store access fault (cause 5/7) with the right mtval | two-cycle ERROR response on load and on store | err_pulse -> mem_exception_valid, cause 5 or 7 | P0
51 | one outstanding | issuing a second transfer before the first completes violates the D-port contract | back-to-back load/store with wait states | strictly one at a time | P0
CONTROL — pipe_ctrl.v
52 | hold table | the Sec.11.4 hold composition decides which stages freeze; a wrong entry either loses or duplicates an instruction | assert each hold source alone and in combination | matches the documented hold table | P0
53 | flush beats hold | a squashed instruction must not be held — it is being discarded anyway | flush and stall on the same register in the same cycle | flush wins per Sec.11.4 | P0
54 | redirect priority | trap > EX > ID; wrong order resumes at the wrong PC | all three redirects asserted together | trap target selected | P0
55 | mem_stall gating | redirects must not fire mid-D-port-wait | assert a redirect while mem_stall is high | redirect deferred until the wait clears | P0
56 | WFI drain-precision | WFI must hold PC, IF/ID AND ID/EX so the younger instruction does not execute during sleep (fixed 2026-07-20) | assert wfi_hold, observe the hold pattern | 1_0_1_0_1_0_0_0_0 — EX/MEM free so older ops drain | P0 | PASS
57 | FORMAL | hold/flush composition is a small, high-consequence lattice | JasperGold FPV: no-lost-instruction and no-duplicate properties | proven, not sampled | P1
CONTROL — csr_file.v
58 | read/write every CSR | an unimplemented or mis-decoded CSR silently reads 0 | sweep the whole implemented address list | each reads back what was written; RO ones reject writes | P0
59 | illegal CSR | access to an unimplemented CSR, or a write to a read-only one, must raise illegal (cause 2) | unimplemented address; write to misa/mip/mintstatus/dsu_ovf | illegal_csr asserted | P0
60 | mstatus push/pop | trap entry must push MIE->MPIE and clear MIE; MRET must pop. Getting this wrong nests interrupts incorrectly | trap then MRET with MIE initially set | MPIE/MIE sequence per Sec.14.4 | P0
61 | minstret accuracy | counts architectural retirement, not register writes — stores and branches retire without writing (fixed 2026-07-20) | run a mixed stream incl. stores, branches and a faulting load | minstret == instructions retired; faulting load NOT counted | P0
62 | mcycle | must free-run every cycle including stalls | count over a stalled window | increments unconditionally | P1
63 | mip.MTIP / mip.MEIP | mip is hardware state; a writable mip is a spec violation and lets firmware fake interrupts | drive mtip and clic pending; attempt to write mip | bit7/bit11 track hardware; write raises illegal | P0
64 | dsu_ovf read-clear | reading 0xBC0 must clear the sticky DSU overflow flag | set overflow, read the CSR twice | first read 1, flag cleared, second read 0 | P0
CONTROL — trap_ctrl.v (highest-consequence block in the core)
65 | EX exception priority | Sec.14.1 order 1>2>3>4>6>11 — wrong order reports the wrong mcause for a genuinely faulting instruction | assert several EX exception sources simultaneously | highest-priority cause wins | P0 | PASS
66 | MEM outranks EX | the older instruction must win; otherwise a younger fault retires an older faulting access | MEM access fault + EX illegal in the same cycle | cause 5/7 taken, mepc from MEM | P0 | PASS
67 | exception beats interrupt | taking an interrupt instead of a pending exception loses the exception permanently | EX illegal + CLIC take_cond together | exception taken | P0 | PASS
68 | mtval per cause | Sec.14.2: 1->PC, 2->instr, 3->PC, 4/6->addr, 5/7->addr, 11/int->0. Wrong mtval breaks the handler | one case per cause | mtval matches the table | P0 | PASS
69 | MTI entry | machine timer must be takeable, ranked below CLIC external, gated by mstatus.MIE (added 2026-07-20) | mtip+mtie with MIE set / clear; MTI vs CLIC together | cause 0x80000007 at mtvec base; CLIC wins when both | P0 | PASS
70 | WFI wake MIE-independent | with MIE clear the hart must still resume after the WFI, not sleep forever | WFI, then assert a pending interrupt with MIE=0 | wfi_hold releases; no trap taken | P0 | PASS
71 | MRET | must pop mstatus and redirect to mepc without entering a trap | MRET after a trap | mret pulse, no trap_enter, redirect to mepc | P0 | PASS
72 | nested / back-to-back traps | a trap arriving during trap entry is the classic lockup-that-does-not-reproduce | assert a second trap source during the entry bubbles | no lost trap, no double entry | P0
73 | FORMAL | this block is small, control-only, and the most dangerous thing in the core — simulation only samples its state space | JasperGold FPV: mutual exclusion of causes, priority ladder, no-trap-lost | properties proven | P0
CONTROL — clic_ctrl.v
74 | level arbitration | a lower-level interrupt pre-empting a higher one breaks the whole priority scheme | sweep irq level vs mintthresh vs mintstatus.mil | take_cond only when level > threshold and > current | P0
75 | shv vectoring | selectable hardware vectoring must read the right mtvt entry | shv set and clear | vector target from mtvt table vs mtvec base | P0
76 | ack handshake | a missing or duplicated ack loses or re-takes an interrupt | take an interrupt, observe ack | exactly one ack pulse with the matching id | P0
Pipeline registers — if_id / id_ex / ex_mem / mem_wb_reg
77 | hold retains | a held stage that does not retain corrupts the in-flight instruction | stall for N cycles | all fields unchanged for N cycles | P0 | PASS
78 | flush bubbles | a flushed stage must drive all write-enables low, not just change the opcode | assert flush | reg_write/mem_write/valid all low; NOP encoding | P0 | PASS
79 | flush beats stall | Sec.11.4 priority | both asserted together | bubble inserted | P0 | PASS
80 | retire tag | valid must be low in a bubble or minstret over-counts (added 2026-07-20) | flush and stall sequences | valid low in every bubble | P0
Integration — garuda_core_top.v
81 | elaboration with real DSU | the frozen Sec.9.2 boundary must hold against real hardware, not just the stub | make elab_core_dsu | clean elaborate, zero warnings | P0 | PASS
82 | EX equivalence stub vs DSU | with dsu_en low the real DSU must be completely inert and inject no X into the result mux | make test_ex and test_ex_dsu | bit-identical results | P0 | PASS
Legend:
Pri P0 = must pass to tape out. P1 = should pass.
Done PASS = TB exists and passes. blank = not written yet.
Status: 6 of 26 core modules have any testbench today.
The strategy doc has no unit section for CSR / trap / privilege — for GARUDA those are the highest-consequence blocks, so they are added here.

## 2 Core Sanity TB
Phase 2 — Core Sanity Testbench
Strategy doc §3. garuda_core_top + AHB-Lite memory models + IRQ stimulus. Self-checking directed sequences, no software toolchain required yet.
# | Test | What could go wrong / what it checks | How I test it | Expected result | Pri | Done
Bring-up
1 | reset & first fetch | if the first fetch is wrong nothing else matters | release reset, watch the I-port | fetch from RESET_VECTOR, PC advances by 4 | P0
2 | I-MEM / D-MEM models | the TB harness itself must be trustworthy before it can judge the DUT | AHB-Lite behavioural slaves with programmable wait states | zero-wait and N-wait both work | P0
One of each instruction class
3 | arithmetic | the base sanity check | ADDI/ADD/SUB/AND/OR/XOR sequence with known operands | self-checking: final register values match | P0
4 | branches | control flow must actually redirect | taken and not-taken of each branch type | correct path executed | P0
5 | jumps | JAL/JALR link register and target | JAL forward/backward, JALR with register base | correct target; ra holds PC+4 | P0
6 | loads/stores | round-trip through the D-port | store then load back at all sizes and offsets | value round-trips with correct extension | P0
7 | M-extension | each of the 8 M ops executes at least once | MUL/MULH/MULHSU/MULHU/DIV/DIVU/REM/REMU | results match reference | P0
8 | CSR access | privilege plumbing works end to end | CSRRW/S/C on mscratch and mstatus | read-modify-write correct | P0
9 | DSU Custom-0 | the accelerator executes inside the real pipeline | a short MAC sequence then readback | register receives the expected accumulator value | P0
Hazards in a real pipeline
10 | RAW back-to-back | forwarding under real timing | dependent ops at distance 1, 2, 3 | correct values, no stall needed beyond load-use | P0
11 | load-use | the one hazard that needs a stall | LOAD then immediate dependent use | one bubble, correct data | P0
12 | branch + hazard | a branch whose condition depends on the previous op | ADD then BEQ on the result | correct direction taken | P0
13 | DSU busy hold | same-accumulator interlock in the real pipeline | back-to-back DSU readbacks on one accumulator | pipeline holds, no lost instruction | P0
Traps and interrupts
14 | ECALL / EBREAK | synchronous trap entry from a real instruction stream | execute each | mepc/mcause/mtval correct, handler entered | P0
15 | illegal instruction | a bad word mid-stream | inject 0xDEADBEEF | cause 2, mtval = the instruction word | P0
16 | misaligned load/store | cause 4/6 from a real address | LW at an odd address | trap taken before the bus transfer | P0
17 | bus error | cause 5/7 from the D-port | D-MEM model returns ERROR | trap with the faulting address in mtval | P0
18 | IRQ mid-stream | an interrupt arriving at an arbitrary point must take at a clean boundary — this is where lockups come from | assert CLIC irq at many different offsets into a loop | trap at an instruction boundary; mepc resumable | P0
19 | MRET resume | the handler must return to exactly the right place | trap then MRET | execution resumes at mepc, state restored | P0
20 | WFI sleep/wake | drain-precise hold plus wake | WFI then interrupt | younger instruction did NOT execute during sleep | P0
Memory timing stress
21 | random wait states | the pipeline must be indifferent to bus latency | randomise I and D wait states 0..8 per access | same architectural result as zero-wait | P0
22 | flush + outstanding fetch | redirect while a fetch is in flight | branch mispredict with I-port wait states | no stale instruction injected | P0
Prerequisite: AHB-Lite behavioural memory models with programmable wait states and ERROR injection.
The strategy doc's diagram shows generic I-MEM/D-MEM models; for GARUDA these must speak AHB-Lite, not OBI or AXI.

## 3 Core ISA-ISS
Phase 3 — Core ISA / ISS Lockstep
Strategy doc §4. riscv-arch-test + riscv-dv against Spike, compared per retired instruction.
# | Test | What could go wrong / what it checks | How I test it | Expected result | Pri | Done
Toolchain bring-up
1 | riscv-gnu-toolchain | everything downstream needs it | install riscv32-elf, compile and link a bare-metal hello | test.elf -> test.hex loads and runs on the DUT | P0
2 | Spike ISS | the golden reference for the whole core | build riscv-isa-sim configured for RV32IM, machine mode only | Spike executes the same hex and logs commits | P0
3 | log comparator | the actual pass/fail engine | script diffing DUT retire log vs Spike commit log per instruction | first divergence reported with PC and instruction | P0
4 | retire trace from RTL | lockstep needs a per-instruction retire signal — the mem_wb retire tag added 2026-07-20 is exactly this | dump PC/instr/rd/rd_value on retire_o | one log line per retired instruction | P0
Compliance
5 | RISCOF setup | the official conformance framework | configure RISCOF with the DUT plugin and Spike as reference | framework runs end to end on one test | P0
6 | rv32ui | base integer conformance | run the full rv32ui arch-test suite | all signatures match the reference | P0
7 | rv32um | M-extension conformance | run the full rv32um suite | all signatures match | P0
8 | privileged / trap tests | machine-mode trap behaviour | the machine-mode subset of arch-test | signatures match | P0
Random instruction streams
9 | riscv-dv bring-up | the tool that finds what you did not think of | configure riscv-dv for RV32IM machine-mode, Spike as reference | one random program generated, compiled and compared | P0
10 | hazard stress | dense back-to-back dependencies | riscv-dv with high dependency density | 1k seeds clean | P0
11 | control stress | dense branches and jumps | riscv-dv branch-heavy configuration | 1k seeds clean | P0
12 | exception stress | random illegal and misaligned accesses | riscv-dv with exception generation enabled | 1k seeds clean; all traps match Spike | P0
13 | interrupt stress | random IRQ injection during random code | riscv-dv interrupt mode + CLIC stimulus | no lockups; mepc always resumable | P0
GARUDA-specific ISS problems (need a decision — see Open Questions)
14 | Custom-0 in Spike | Spike will trap DSU instructions as illegal, so any program containing one diverges immediately | extend Spike via its custom-extension hook, calling the DSU golden model; or exclude DSU instrs from the compare | DSU instructions retire in Spike with correct effects | P0
15 | CLIC in Spike | base Spike models CLINT, not CLIC. GARUDA's entire trap architecture is CLIC-based | decide: model CLIC in Spike, or verify CLIC traps by directed + formal only and exclude them from lockstep | documented decision, agreed with the coach | P0
16 | mip layout | GARUDA uses MEIP as a CLIC pending summary — compliance tests that poke mip/mie may flag it | run the privileged suite and triage any mip/mie failures | either conformant, or a documented deliberate deviation | P1
Benchmarks
17 | Dhrystone / CoreMark | a long real program is a different stress than random streams | compile and run to completion | correct result; no deadlock; performance recorded | P1
This phase is where most core bugs will actually be found.
The retire tag added to mem_wb on 2026-07-20 is the signal a lockstep harness needs — that work is a prerequisite, not a counter fix.
Red rows are GARUDA-specific blockers that need a decision before the phase can start.

## 4 SoC no Core
Phase 4 — SoC Verification without Core
Strategy doc §5. BLOCKED: the SoC RTL does not exist yet.
# | Test | What could go wrong / what it checks | How I test it | Expected result | Pri | Done
This entire phase is BLOCKED
1 | RTL does not exist | rtl/ahb, rtl/apb, rtl/ahb2apb, rtl/uart, rtl/gpio, rtl/i2c, rtl/spi_master, rtl/spi_slave, rtl/pwm, rtl/timers, rtl/plic, rtl/clic, rtl/dma, rtl/brom, rtl/isram, rtl/dsram are all empty directories | n/a | cannot start until the SoC RTL is written | P1 | BLOCKED
Planned scope (for when it unblocks)
2 | bus agent | the coach's template assumes AXI; GARUDA is AHB-Lite | UVM AHB-Lite master agent (Cadence VIP) in place of the core | agent drives the interconnect | P1
3 | address map decode | wrong decode sends a transfer to the wrong slave | walk every slave's address range and the gaps between | each access lands on the intended slave; gaps error cleanly | P1
4 | register access | RW/RO/W1C behaviour per peripheral register | read/write every addressable register | 100% register coverage; field behaviour correct | P1
5 | AHB-to-APB bridge | protocol conversion and the clock-domain crossing (200MHz core vs 100MHz peripheral) is a classic escape | randomised traffic across the bridge | no lost or duplicated transfers; CDC clean | P1
6 | interrupt routing | a peripheral interrupt that never reaches the controller is invisible until silicon | generate each peripheral event | every source verified end-to-end to the controller input | P1
7 | multi-master arbitration | core I-port, core D-port and DMA all contend | concurrent traffic from all masters | no starvation, no protocol violation | P1
The strategy doc notes phase 4 can run in parallel with 1-3.
For GARUDA it cannot: every SoC RTL directory is empty. Listed here so the dependency is explicit rather than implied.

## 5 Full SoC
Phase 5 — Full SoC with Core
Strategy doc §6. BLOCKED: depends on Phase 4.
# | Test | What could go wrong / what it checks | How I test it | Expected result | Pri | Done
This entire phase is BLOCKED — depends on Phase 4
1 | prerequisite | needs SoC RTL and a passing Phase 4 | n/a | cannot start | P1 | BLOCKED
Planned scope
2 | boot from BROM | if it does not boot, nothing else runs | reset into the boot ROM | reaches main() | P1
3 | memory tests | TCM integrity | march and walking-ones over 384KB TCM | no bit errors | P1
4 | peripheral loopback | end-to-end through real firmware | UART/SPI/GPIO loopback tests in C | data round-trips | P1
5 | timer interrupt in C | the MTI path exercised by real firmware | set mtimecmp, enable, wait | handler entered at the right time | P1
6 | DSU firmware kernel | the APF collision-avoidance kernel is the point of the chip | run the real APF routine on real data | output vector matches the Python reference | P0
7 | long run stability | deadlocks appear at hour scale, not test scale | multi-million-cycle random + firmware soak | no deadlock, no protocol stall beyond bounds | P1

## Coverage
Coverage & Signoff Criteria — Core
The strategy doc defines signoff as coverage closure + bug burn-down, not 'it ran once'.
# | Test | What could go wrong / what it checks | How I test it | Expected result | Pri | Done
The coach's signoff bar is coverage, not 'the test passed'
1 | current state | there are ZERO covergroups anywhere in the project today — every existing TB is a pass/fail $display | audit tb/ for covergroup declarations | this row closes when every P0 block has a covergroup | P0
Functional coverage — per block
2 | decode_control | the biggest cross in the design | cross opcode x funct3 x funct7 | all legal combinations hit | P0
3 | load/store | size x offset is where alignment bugs live | cross size x address[1:0] x signed/unsigned | all combinations hit | P0
4 | ALU | corner values, not just random | bins on 0, 1, -1, 0x7FFFFFFF, 0x80000000; shift amounts 0/1/31/32+ | all bins hit | P0
5 | hazards | dependency patterns | cross {rs1 hazard, rs2 hazard, both} x {ALU->use, LOAD->use, STORE->use} x distance 1/2/3 | all bins hit | P0
6 | traps | every cause, and the priority pairs | bins per mcause; cross of simultaneous exception sources | every implemented cause taken at least once | P0
7 | CLIC | level vs threshold vs current level | cross irq level x mintthresh x mintstatus.mil x shv | arbitration space covered | P0
8 | AHB protocol | wait-state and response buckets | bins on wait-state count 0/1/2/>2 and HRESP OKAY/ERROR | all buckets hit on both ports | P0
Code coverage
9 | statement/branch/toggle | the coach's bar is 95% with waivers | Xcelium code coverage across the full regression, merged in vManager | >=95%, every exclusion justified in writing | P0
10 | waiver review | an unjustified waiver is a hole with paperwork | review every exclusion with the coach | each waiver has a documented reason | P0
Regression
11 | seed count | one passing seed proves nothing | riscv-dv N-seed regression, N per the coach's guidance (1k-10k) | stable pass rate across N seeds | P0
12 | bug burn-down | signoff is closure, not test count | track P0/P1 bugs found vs closed over time | all P0/P1 closed; burn-down curve flat before tapeout | P0

## Infrastructure
Infrastructure & Tools — Core
What we have, what we need, and who provides it.
# | Test | What could go wrong / what it checks | How I test it | Expected result | Pri | Done
Simulators
1 | Cadence Xcelium | the signoff simulator | xrun -f <filelist>; make SIM=xrun <target> | available — all Cadence tools licensed | P0 | HAVE
2 | Vivado xsim | fallback used for the 2026-07-20 fixes because xrun was not on PATH on this machine | make SIM=xsim <target> | works; xrun path still needs one confirming run | P1 | PARTIAL
3 | JasperGold | formal for the control blocks | FPV on pipe_ctrl, trap_ctrl, forward_unit | available — high value, not yet used | P1 | HAVE
4 | vManager | coverage merge and regression management | merge coverage across all phases | available, not yet used | P0 | HAVE
RISC-V toolchain (all open source, none installed yet)
5 | riscv-gnu-toolchain | compiles every test program | riscv32-elf precompiled release; -elf for bare metal | riscv32-unknown-elf-gcc on PATH | P0 | TODO
6 | Spike (riscv-isa-sim) | the golden ISS for lockstep | build for RV32IM machine-mode; NEEDS Custom-0 + CLIC work | runs the same hex as the DUT and logs commits | P0 | TODO
7 | RISCOF | compliance framework | pip install riscof; DUT plugin + Spike reference plugin | runs riscv-arch-test end to end | P0 | TODO
8 | riscv-dv | constrained-random instruction generator | chipsalliance/riscv-dv, SV/UVM, Spike as reference | generates and compares random streams | P0 | TODO
Verification IP
9 | AHB-Lite VIP | do not hand-write bus models — the VIP's protocol assertions catch what a hand model allows | Cadence AHB VIP on I-port and D-port | protocol checking active in every core-level run | P0 | TODO
10 | unit framework from coach | the strategy doc offers deeptech360/1tops_vyom_framework and an instruction encoder/decoder — building our own first means rewriting later | ASK THE COACH for access before writing more unit TBs | framework in hand and adopted | P0 | ASK
GARUDA-owned models
11 | DSU golden model | the core cannot be lockstepped against Spike until Spike understands Custom-0, which needs this model | tools/golden/DSU_Golden.py — see the separate DSU plan | DONE — cycle-accurate, validated against RTL 2026-07-20 | P0 | HAVE
12 | APF reference | the collision-avoidance kernel needs a reference too | Python model of the APF routine | used in Phase 5 firmware check | P1 | TODO
HAVE = available now. TODO = not installed. ASK = needs the coach. PARTIAL = works with caveats.

## Open Questions
Open Questions & Decisions — Core
Putting open questions in the submitted plan is deliberate — the same discipline the project already applies to spec errata.
# | Test | What could go wrong / what it checks | How I test it | Expected result | Pri | Done
Decisions needed from the coach
1 | Spike + Custom-0 | Spike traps DSU instructions as illegal, so lockstep diverges on any program containing one | proposal: extend Spike via its custom-extension hook to call DSU_Golden.py's DSUModel | agreed approach before Phase 3 starts | P0 | ASK
2 | Spike + CLIC | base Spike models CLINT, not CLIC; GARUDA's whole trap architecture is CLIC-based | proposal: verify CLIC traps by directed + formal, exclude from lockstep | agreed approach | P0 | ASK
3 | CLIC vs PLIC | both rtl/clic and rtl/plic exist as empty directories. The core is CLIC-based; the coach's reference SoC uses CLINT+PLIC | ask which the SoC will actually carry | documented decision — it changes the trap architecture | P0 | ASK
4 | AXI vs AHB in the strategy doc | phases 4 and 5 of the strategy assume AXI/AXI-Lite/APB; GARUDA is AHB-Lite. Section 2.8 also references OBI (gnt/rvalid) which GARUDA does not use | confirm the AHB translation of those phases is acceptable | agreed | P1 | ASK
5 | unit framework | the doc offers a framework; adopting it late means rewriting the unit TBs | request deeptech360/1tops_vyom_framework access | framework in hand before more unit TBs are written | P0 | ASK
6 | formal is not in the strategy doc | JasperGold is licensed and the control blocks are ideal FPV targets — worth adding as a layer | propose FPV on pipe_ctrl, trap_ctrl, forward_unit | agreed scope | P1 | ASK
Schedule reality
7 | RTL freeze date passed | README targets RTL freeze end of June; today is 2026-07-20. Core and DSU RTL are complete and elaborate together, so the RTL side is essentially met — but the slip is now entirely verification debt against a GDSII date of end-October | re-plan with the coach using this workbook | agreed, dated plan with owners | P0 | ASK
Cross-reference
8 | DSU has its own plan | block II is verified separately; its open RTL findings (FLAG-A, FLAG-C) are tracked there | see tb/dsu/GARUDA_DSU_Verification_Plan.xlsx | both plans reviewed together | P0